## Sheet1
Task | Sub Task | Start Date | End Date | Comments | Status
Essential GUI Revisions | Handling missed (as in too late) hit attempts | - | - | - | complete
| Build confidence/skill 2d matrix (likekly confidence in hit vs precision of hit) | - | 2020-02-03 | Not yet built | incomplete
| Build margin of error toggle (essentially changes the mole size) |  | 2020-01-25 | Requires testing, otherwise complete | incomplete
| Scoring refreshed every hit |  |  | - | complete
Nice to Have GUI Revisions | Instructions screens |  |  | Performed as part of 'competing' coursework | complete
| Demographics etc. screen |  |  | Performed as part of 'competing' coursework | complete
| Clean code (code base is a little messy |  |  | ongoing effort, trying to keep manageable | incomplete
| Increase 'board' size, number of moles etc. |  |  | deprioritised | Not Started
Instructions | Author unambiguous instructions for lay audience | 2020-02-10 | 2020-02-15 | - | Not Started
Analyse Approach Definition | 2-3 individuals to source feed | 2020-02-20 | 2020-02-25 | - | Not Started
| Deceide: low number participants high reps vs high number of participants low reps | 2020-03-01 | 2020-03-08 | - | Not Started
Run Tests | Source participants | 2020-03-13 | 2020-03-28 | - | Not Started
| Execute tests | 2020-03-28 | 2020-04-17 | - | Not Started
Analyse Results | Iteration 1 | 2020-04-17 | 2020-04-27 | - | Not Started
| Iteration 2 | 2020-05-02 | 2020-05-17 | - | Not Started
Write Up | Thesis 1st Draft | 2020-05-18 | 2020-06-09 | - | Not Started
| Thesis 2nd Draft (assumes comments from BDM or equiv) | 2020-06-17 | 2020-07-04 | - | Not Started
| Thesis Final (final deadline the 19th of August) | 2020-07-04 | 2020-07-11 | - | Not Started
| Paper write up | 2020-07-18 | 2020-08-18 | - | Not Started